JEA Tabletop Smart Grid Trainer

Union University Senior Design Project — Scope of Work & Timeline

# 1. Project Overview

Jackson Energy Authority (JEA) is sponsoring a senior design team to build a tabletop distribution automation trainer that mirrors real utility switching and restoration behavior. Wall power (120VAC) feeds a main distribution board with breakers out to each source, forming a backbone of protective and switching devices (breakers, reclosers, and fuses) between two source ends. Several fault-injection points are distributed along that backbone, each tied to the protective device that should respond to a fault there.

The concept also includes: an alternate source (DER) tied into the backbone through its own protective device; a normally-open tie switch providing an alternate restoration path once a section is isolated; one or more load laterals (status indicator, variable load, and test points, potentially represented by 3D-printed houses) so the effect of a fault is visible; dual fault control via both a physical pushbutton on the table and an HMI; a 2D plan view rendered on vinyl or wrap as a visual backdrop for the panel; and a power system analysis pass (e.g. in Milsoft) to validate the design.

# 2. Scope of Work — Ordered Task List

Tasks are grouped into two parallel tracks after the design phase — Hardware/Electrical/Structural and Software/Controls — which converge at integration. This lets coding and bench-testing of FLISR logic start well before the physical build is finished.

## Phase 0 – Kickoff

- Review project background, problem statement, and JEA's real-world FLISR process

- Establish communication plan and meeting cadence.

                - - Start off bi-weekly teams meeting, once a month in-person meeting. Obviously can meet as needed depending on need.

- Determine file sharing methods

            - - google drive for centralized file repository

## Phase 1 – Requirements & Research

- Research RTAC/Axion fundamentals and FLISR logic sequencing

- Define functional requirements and success criteria for the demo

- Document constraints (budget, lab space, safety, timeline)

- $10k budget allowance ($3k for Axion, $2500 for RTAC), portability

## Phase 2 – Conceptual Design

- Electrical: draft one-line diagram — backbone of protective/switching devices between two sources, fault-injection points tied to each device, a DER tie, and a normally-open restoration tie

- Voltage-level decision (should be 120VAC to accommodate metering card for Axion) and RTAC/HMI communication architecture

- Load lateral design: status indicators, variable load and test points

- Fault-control scheme: physical pushbutton plus HMI, and how each maps to a fault-injection point

- Structural: tabletop/enclosure layout, panel mounting, portability for demo day, and a 2D plan-view graphic for a vinyl/wrap panel backdrop

- Determine a model scale for the design

- How do we visualize the electric path? Red “paint” to simulate locates

- Preliminary Design Review (PDR)

## Phase 3 – Component Selection

- Select protective/switching devices, RTAC/PLC hardware (RTAC and Axion purchased), sensors, indicator lights, wiring/connectors, power supply, enclosure materials

- Draft Bill of Materials (BOM) and budget estimate

- Begin controls/software architecture planning in parallel

## Phase 4 – Material Acquisition

- Sponsor/faculty sign-off on BOM and budget

- Order Material

          - - Will have to be purchased with JEA P-card or PO

- Begin controls coding — logic can be bench-tested independent of hardware arrival

## Phase 5 – Structural Build-Out

- Fabricate frame/panel and mounting hardware

- Begin 3D printing components to scale

        - - need multiple house layouts

- Fit-check components as they arrive

## Phase 6 – Electrical Assembly & Wiring

- Wire panel point-to-point per the one-line diagram

- Label all wiring and verify against design before energizing

- Build out HMI

## Phase 7 – Integration

- Combine hardware and controls; first integrated power-up

## Phase 8 – Functional Testing

- Run full FLISR scenario end-to-end: fault → isolation → restoration

## Phase 9 – Troubleshooting & Refinement

- Iterate on any issues found in testing until the demo is stable and repeatable

## Phase 10–11 – Documentation & Reporting

- Complete Milsoft Design and Simulation of Model

- Draft technical report, as-built one-line diagram, code documentation, and demo/user guide

- Review and Present with JEA (even with Seniors and other divisions)

## Phase 12 – Final Demo Prep

- Rehearse the demo, polish presentation, finalize before end of March

- Attend UU event (April 6th 2027)

# 3. Project Timeline

Target completion: March 27. Table below shows suggested phase sequencing, target dates, which track owns the task, and the associated milestone or deliverable.

| Phase | Task | Target Dates | Track | Milestone / Deliverable |
| --- | --- | --- | --- | --- |
| 0 | Project kickoff, review of problem statement & background |  | All | Kickoff meeting held; roles assigned |
| 1 | Requirements gathering & research (FLISR concepts, RTAC basics, similar trainer builds) |  | All | Requirements doc drafted |
| 2 | Conceptual design – electrical (one-line diagram: backbone, fault-injection points, DER tie, normally-open restoration tie, voltage level, RTAC/HMI comms) |  | Hardware/Electrical | Draft one-line diagram |
| 2 | Conceptual design – structural/mechanical (tabletop layout, enclosure, portability, panel mounting, 2D plan-view vinyl/wrap graphic) |  | Structural | Draft layout drawing |
| — | Preliminary Design Review (PDR) with JEA | Week of Oct 5 | All | Milestone: design approved to proceed |
| 3 | Component selection (protective devices, RTAC/PLC hardware, sensors, indicators, wiring, enclosure materials, power supply) |  | Hardware/Electrical | Bill of Materials (BOM) drafted |
| 3 | Begin controls/software architecture & logic planning (FLISR sequencing, HMI concept) |  | Software/Controls | Logic flow diagram |
| — | Budget & BOM approval (sponsor sign-off) |  | All | Milestone: BOM approved, PO process started |
| 4 | Material acquisition / procurement (order long-lead items first — RTAC, PLC, switchgear) |  | Hardware/Electrical | Materials on order/received |
| 4 | Controls coding begins (can bench-test logic independent of hardware) |  | Software/Controls | Bench-tested FLISR logic |
| 5 | Structural build-out (frame/panel fabrication, mounting hardware) |  | Structural | Physical structure complete |
| 6 | Electrical assembly & wiring (point-to-point per one-line, labeling, panel wiring) |  | Hardware/Electrical | Panel wired & inspected |
| — | Winter break — no scheduled work | Dec 10 – Jan 7 | — | — |
| 7 | System integration (hardware + controls combined) |  | All | First integrated power-up |
| 8 | Functional testing of full FLISR scenario (fault → isolation → restoration) |  | All | Successful end-to-end demo run |
| 9 | Troubleshooting & refinement (iterate on issues found in testing) |  | All | Stable, repeatable demo |
| 10 | Documentation (technical report, as-built one-line, code docs, user/demo guide) |  | All | Draft final report |
| 11 | Final report review with faculty/sponsor; revisions |  | All | Report finalized |
| 12 | Demo rehearsal & polish | First of March | All | Rehearsed, repeatable demo |
| — | Final presentation / demo day | April 6th, 2027 | All | Milestone: Project complete |

# 4. First Meeting Agenda

- Introductions and project background — why JEA, the real-world problem this mirrors

- Walk through scope of work and the ordered task list

- Walk through the proposed timeline and key milestones (PDR, BOM approval, integration, demo day)

- Review budget range and procurement process (who submits POs, approval turnaround, JEA point of contact)

- Set communication plan: meeting cadence, shared drive/GitHub for code and docs, primary chat tool

- Discuss safety expectations (low-voltage design intent, lab/shop safety, PPE as applicable)

- Confirm faculty advisor's role and availability

- Discuss software needed and give them access

- Open Q&A / concerns

# 5. Additional Notes for Kickoff

- Safety: voltage level is left to the team, but any design should minimize hazard — this is a strong candidate for a documented design decision in the final report.

- Load representation: decide early whether load elements (e.g. 3D-printed houses) are structurally part of the circuit or simply house a resistor/LED fed by wiring — this affects both the electrical design and the fabrication approach.

- Long-lead items: RTAC/Axion hardware and any custom switchgear should be identified and ordered as early as possible (Phase 3–4) to avoid delaying the build track.

- Parallel tracks: keep controls/software work moving during procurement and structural build — don't let coding wait on hardware arrival.

- University lab schedule: confirm shop/lab access hours and any equipment reservation process before the build phase starts.

- Risk items to flag early: shipping delays on specialty components, lab access conflicts around midterms/finals, and scope creep beyond a tabletop demo.

- Success criteria for demo day: a repeatable fault → isolation → restoration sequence the team can run live, plus a clear one-line diagram and short explanation for visitors.